## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Drawing App
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Ba Nguyen
Project start date: | 2024-01-07 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
Scrolling increment: | 5 | time axis 2024-01-12 to 2024-03-07
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-01-12 to 2024-03-07
Project development
Project charter | Goal | Name | 25% | 2024-01-07 | 3
Research | Milestone |  |  | 2024-01-12 | 1 | bar: 2024-01-12
Projections | Low Risk |  | 50% | 2024-01-04 | 10
Stakeholders | Milestone |  |  | 2024-01-27 | 1 | bar: 2024-01-27
Review | Med Risk |  | 10% | 2024-01-13 | 6
Contracts
Proposals | High Risk |  | 60% | 2024-01-13 | 13
Document review | On Track |  | 50% | 2024-01-15 | 9
Bid date | Low Risk |  | 33% | 2024-01-20 | 11
Award date | Milestone |  |  | 2024-01-22 | 1 | bar: 2024-01-22
Finalize |  |  |  | 2024-01-23 | 24
Design
Feasibility study | On Track |  |  | 2024-01-22 | 4
Submit permit applications | Med Risk |  |  | 2024-01-25 | 14
Design proposal | On Track |  |  | 2024-02-09 | 6
Materials | Goal |  |  | 2024-02-13 | 3 | 2024-02-13: 2; 2024-02-14: 2; 2024-02-15: 2
Equipment | Low Risk |  |  | 2024-01-13 | 19
Testing
Environment |  |  |  | 2024-02-16 | 15
System test |  |  |  | 2024-03-01 | 5
Issues/bugs | Milestone |  |  | 2024-04-12 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2024-01-07 |  |  |  |  | January | [20 empty] | February | [27 empty] | March
Scrolling increment: | 5 | time axis 2024-01-12 to 2024-03-07
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
TITLE 1
Task 1 | Goal | Name | 25% | 2024-01-07 | 3
Task 2 | Milestone |  |  | 2024-01-12 | 1 | bar: F
Task 3 | Low Risk |  | 50% | 2024-01-04 | 10
Task 4 | Milestone |  |  | 2024-01-27 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2024-01-13 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-01-13 | 13
Task 2 | On Track |  | 50% | 2024-01-15 | 9
Task 3 | Low Risk |  | 33% | 2024-01-20 | 11
Task 4 | Milestone |  |  | 2024-01-22 | 1 | bar: M
Task 5 |  |  |  | 2024-01-23 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-01-22 | 4
Task 2 | Med Risk |  |  | 2024-01-25 | 14
Task 3 | On Track |  |  | 2024-02-09 | 6
Task 4 | Goal |  |  | 2024-02-13 | 3 | T: 2; W: 2; T: 2
Task 5 | Low Risk |  |  | 2024-01-13 | 19
TITLE 4
Task 1 |  |  |  | 2024-02-16 | 15
Task 2 |  |  |  | 2024-03-01 | 5
Task 3 | Milestone |  |  | 2024-04-12 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Drawing App
[6 empty] | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Ba Nguyen
Project start date: | 2023-12-18 |  |  |  |  | December | [13 empty] | January | [34 empty] | February
Scrolling increment: | 0 | time axis 2023-12-18 to 2024-02-11
Milestone description | Category | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
WEEK 1
Brainstorm features to implement | On Track | 100% | 2023-12-18 | 1
Research implementation for layers | On Track | 100% | 2023-12-19 | 3
WEEK 2 |  |  | 2023-12-23
work on layers function | On Track | 50% | 2023-12-25 | 7
WEEK 3
work on layers function | On Track | 20% | 2024-01-01 | 3
Research implementation for eraser | On Track | 100% | 2024-01-03 | 1
work on eraser function | On Track | 50% | 2024-01-04 | 3
WEEK 4
work on strokeWeight() for eraser and maybe other tools | Med Risk | 0% | 2024-01-08 | 2
change layers and add HTML/CSS | High Risk | 0% | 2024-01-10 | 3
WEEK 5
Research Undo/Redo feature | Low Risk | 0% | 2024-01-15 | 2
Plan out how to implement the feature | Low Risk | 0% | 2024-01-17 | 1
ask for user opinion on features so far | Low Risk |  | 2024-01-18 | 1
WEEK 6
work on Undo/Redo feature | High Risk | 0% | 2024-01-22 | 5
WEEK 7
Use this week to work on previous features if needed | Med Risk | 0% | 2024-01-29 | 4
WEEK 8
Research shape tool | Low Risk | 0% | 2024-02-05 | 2
Plan out how to implement the feature | Low Risk | 0% | 2024-02-08 | 1
WEEK 9
work on shape tool | High Risk | 0% | 2024-02-15 | 3
user feedback | Low Risk | 0% | 2024-02-19 | 1
WEEK 10
finalize undo/redo tool | Med Risk | 0% | 2024-02-26 | 2
work on shape tool | Med Risk | 0% | 2024-02-29 | 2
test all tools so far | Low Risk | 0% | 2024-03-02 | 1
WEEK 11
polish all tools | Med Risk | 0% | 2024-03-04 | 5
WEEK 12
Submit final work | Goal |  | 2024-03-11